## gate 0
Gate 0 (opportunities) checklist	Subquestions and notes.
Problem(s)	The core problem/issue that customers are experiencing, and that we want to try solve.
What's already in the market (ie existing alternatives)	Products or services already in the market.
Value proposition	How what we're building is different from existing offers, and why people would want to use/purchase it.
Competitive advantage	OPTIONAL. Our/the product's competitive advantage over existing alternatives.
Customers, possibly early adopters	Potential customer groups/segments, including those who might be involved in early development/adoption of the product.
Revenue streams	OPTIONAL. How the product earns money / the sources of the product's earnings.
Channels	How we'll reach potential / existing customers.
Solution(s)	Potential solution(s) to the problem(s), taking into account all of the above factors.

Criteria (_how_ it's considered)
Team review	The team will review and give their feedback on the initial lean canvas. How can we break thsi down to a smaller opportunity. Could this be dependant on another venture which could be created as a spin off
Board: conflict of interest	The board examines each venture, identifying potential conflicts of interest and (if necessary) vetoing any potentially problematic ventures, or changing a venture's direction.

## gate 1
Gate 1 (lean canvas) checklist	Subquestions and notes.
A completed lean canvas / (as much as is possible - living documents so we should expect them to change)	All fields to be filled in.
Potential/actual collaborators identified	Focus on end users - validate the problem and need (see questions below). / Be discrete - the names of organisations, not their sector. We're validating the canvases, so try to choose appropriate people to validate with (eg not just random people in the street, but people who know about this stuff, etc).
Problem validated with at least 3 potential end users (ie 3 humans).	Questions to ask of each potential end user: / * [Problem] Here's what we understand of the problem people are facing. What do you think? Is this something you've encountered? What are we missing? / * [Solution] Here's what we think could help solve these problems. What do you think? Is it too complicated, or too simple? What are we missing? / * [Advantage] Is there anyone else out there that offers this, or that you're talking with? / * [Revenue streams] What does it currently cost you to solve this problem (if you are)? / * [Key metrics] How do/would you know if your problem is getting better? / * [Channels] Are you part of any industry or professional groups? / What would your peers think of this venture? / Is this something you'd like to be involved in? / And finally, do you know anyone else who has this problem?
Data sources (potential or actual) identified	Ideally, actual data source names - vague is less good, but acceptable. And only if the venture requires data.
Riskiest assumption	Thing most likely to fail, or least known about.
All canvases put in front of team for feedback, and approved by team after feedback incorporation	This is when scoring happens, too.
Venture lead identified (per venture, for continuity)	Single point of contact for the venture.

Criteria (_how_ it's considered)
Venture Managers	If they don’t care about it deeply, it could influence its chances of success.
Is the market ready for this product now, or later?	We prefer later, as this factors in the time to develop a product, and anticipating the market being ready.
Impact to New Zealand	Considering the positive and negative effects.
Value	After the further customer research and validation, is there still value?
Is this a Data Ventures thing?	Sometimes we find, when validating further, that this another organisation’s initiative and not ours, and it’s important to identify early.
Revenue	Has revenue stream(s) been identified and validated?

Scoring
Value	Output of doing, revenue, value to NZ, non-commercial value.
Risk	The knowns related to the venture of what we could face.
Complexity	The unknowns related to the venture
Effort	Investment of doing this i.e. time and resource
Acquisition	Investment of what we don't have to acheive this venture, i.e. data sources, technology

## gate 2
Gate 2 (MVP / proof of concept) checklist	Subquestions and notes.
Validated business model	A validated business model will contain (at minimum) the following information.
- Identify paying customer(s)	Organisations/individuals who will financially support the venture.
- Wireframes/concepts	Description of venture. Visual prototypes for how the product will look and work (eg basic UI) if output involves visual elements.
- Technical design	Design setting out the datasets, platform(s) / product(s), frontend and / or integrations we need to acquire / build.
- User stories	Stories that detail the features and functions of the product to understand what needs to built and helps estimate its size and what we can deliver.
Privacy impact assessment ("privacy by design" is a core principle)	Engage with Stats NZ privacy officer(s) and Privacy Commission to check for privacy issues, risk areas etc.
Health and safety	Considerations around any health and safety risks and obligations and who they sit with.
JV/partnership(s)	JVs (joint ventures) / partnerships will involve (at minimum) the following elements.
- Identified partner(s)	Identified partner organisations with which to work on building and releasing the product.
- Confirmed at least one partner	At least one confirmed partner organisation.
- Resourcing requirements (roles and responsibilities)	From the Stats NZ, DV and partner(s) sides.
- Early draft commercial documents	Letter of intent / indication of terms / IP (intellectual property) etc.
Assessment of risks and impacts on Stats NZ /DV / partners	An assessment of any possible risks or impacts for any organisations involved in the venture.
Communications	Any external/internal communications that need to be done to ensure everyone's on side, appropriately informed, etc.
KPIs	KPIs (key performance indicators) are the measurables for the commercial and non-commercial aspects of ventures.
- Customer value	Get the customer to rate the value and viability of this venture
- Commercial value	Checking the cost of overheads vs revenue/non-financial benefit. Next step to something else (i.e. the venture(s) dependant on this or what could be launched off of this)
Financial model / forecast	A model / forecast of how the venture's finances will work.
Pitch deck	The output document for all the above criteria.

Criteria (_how_ it's considered)
Chosen partner(s)	Board decides using its own criteria.
Updated scoring	Update the scoring done in field 1 to see if it's still of value after proof of the concept.

Scoring
Value	The output of the venture, including (but not limited to) revenue, value to NZ, and non-commercial value.
Risk	Known risks related to the venture.
Complexity	Unknowns related to the venture.
Effort	The time and people-based investment needed.
Acquisition	What we may need to buy, eg data sources, technology.