## gate 1
Gate 1 (lean canvas) checklist | Subquestions and notes.
A completed lean canvas (as much as is possible - living documents so we should expect them to change) | All fields to be filled in.
Potential/actual collaborators identified | Focus on end users - validate the problem and need (see questions below). Be discrete - the names of organisations, not their sector. We're validating the canvases, so try to choose appropriate people to validate with (eg not just random people in the street, but people who know about this stuff, etc).
Problem validated with at least 3 potential end users (ie 3 humans). | Questions to ask of each potential end user: * [Problem] Here's what we understand of the problem people are facing. What do you think? Is this something you've encountered? What are we missing? * [Solution] Here's what we think could help solve these problems. What do you think? Is it too complicated, or too simple? What are we missing? * [Advantage] Is there anyone else out there that offers this, or that you're talking with? * [Revenue streams] What does it currently cost you to solve this problem (if you are)? * [Key metrics] How do/would you know if your problem is getting better? * [Channels] Are you part of any industry or professional groups? What would your peers think of this venture? Is this something you'd like to be involved in? And finally, do you know anyone else who has this problem?
Data sources (potential or actual) identified | Ideally, actual data source names - vague is less good, but acceptable. And only if the venture requires data.
Riskiest assumption | Thing most likely to fail, or least known about.
All canvases put in front of team for feedback, and approved by team after feedback incorporation | This is when scoring happens, too.
Venture lead identified (per venture, for continuity) | Single point of contact for the venture.
Venture | End users
Shoppin' | Hospitality and retailers - Jonny McKenzie, who owns cafes and bars around Wellington. Also Asantha Wijeyeratne.
Data science brokerage | Universities and small agencies - Ewan Howden, director of acquisition at EdNZ. Michael O'Dea, CDHB (aimee's already briefly run the idea past him). Tangi Utikere, Deputy Mayor Palmerston North.
NZBN | Business, banks. Lewis Billinghurst at Westpac, David Bell at ASB.
Location data | Councils, banks, tourism agencies. Steven Horn, CE of Tourism NZ, MCDEM.
Used cars | Potential partners: John Holt, part-owner of Putti, and Jason at DotLovesData. End user: anyone who's bought or sold a second-hand car.
Dynamic rates | Sean at WCC, Sheryl at PNCC, Eli Chadwick (mum is mayor of Rotorua). Contact RetailNZ / BusinessNZ, etc.
Proof of purchase | Payment side: PayMark, SmartPay, EFTPOS NZ. Retailer side: Vend, Whizzbang.
Standard for accounts | Tristan Will, Ian Fay (partner at Deloitte), Steven Nicholas (partner at Deloitte), Owen Gibson (partner at PWC), Gavin Holly (KPMG). Also Sam Daish (Xero), Byron McLean (Xero), Ben Ross (MYOB).
Community data centre | Auckland Forecasting Network, Palmerston City Council, National Council of Women (Vanisa), Michael O'Dea (CDHB), Ministry for Pacific Peoples.
Aerial surveys | Partners: AirNZ, John Holt (private pilot), Simon Holdsworth (private pilot). Council, Jamey Kruger (homes.co.nz), DairyNZ, John Hart (@farmgeek), people from http://www.stuff.co.nz/business/farming/discovery/95906996/pasture-measurement--the-new-technology. See flightradar24. Nearmap is Aussie counterpart of this initiative. NZi3 (Blair to intro me).
Risk modelling | Drew to give aimee some bank/insurer names.

## gate 2
Gate 2 (MVP) checklist | Subquestions and notes.
Validated business model
- Identify paying customer(s)
- Wireframes/concepts
- Technical design | Validates what datasets one needs, what platform product one needs to build, what frontend and/or integrations one needs.
Privacy impact assessment ("privacy by design" is a core principle). | Contact Privacy Commission at the start to check for privacy issues, risk areas etc.
Identify JV/partnership opportunities
Identify JV/partnership/resourcing requirements (roles)
Updated JV/partnership documents (if required)
Assessment of risks and impacts on Stats NZ/DV/partners
Communications | Any external/internal communications that need to be done to ensure everyone's on side, appropriately informed, etc.
Pitch deck