## gate 1
Gate 1 (lean canvas) checklist | Subquestions and notes.
A completed lean canvas (as much as is possible - living documents so we should expect them to change) | All fields to be filled in.
Potential/actual collaborators identified | Focus on end users - validate the problem and need (see questions below). Be discrete - the names of organisations, not their sector. We're validating the canvases, so try to choose appropriate people to validate with (eg not just random people in the street, but people who know about this stuff, etc).
Problem validated with at least 3 potential end users (ie 3 humans). | Questions to ask of each potential end user: * [Problem] Here's what we understand of the problem people are facing. What do you think? Is this something you've encountered? What are we missing? * [Solution] Here's what we think could help solve these problems. What do you think? Is it too complicated, or too simple? What are we missing? * [Advantage] Is there anyone else out there that offers this, or that you're talking with? * [Revenue streams] What does it currently cost you to solve this problem (if you are)? * [Key metrics] How do/would you know if your problem is getting better? * [Channels] Are you part of any industry or professional groups? What would your peers think of this venture? Is this something you'd like to be involved in? And finally, do you know anyone else who has this problem?
Data sources (potential or actual) identified | Ideally, actual data source names - vague is less good, but acceptable. And only if the venture requires data.
Riskiest assumption | Thing most likely to fail, or least known about.
All canvases put in front of team for feedback, and approved by team after feedback incorporation | This is when scoring happens, too.
Venture lead identified (per venture, for continuity) | Single point of contact for the venture.

## gate 2
Gate 2 (MVP) checklist | Subquestions and notes.
Validated business model | A validated business model will contain (at minimum) the following information.
- Identify paying customer(s) | Organisations/individuals who will financially support the venture.
- Wireframes/concepts | Description of venture. Visual prototypes for how the product will look and work (eg basic UI) if output involves visual elements.
- Technical design | Design setting out the datasets, platform(s) / product(s), frontend and / or integrations we need to acquire / build.
- User stories | Stories that detail the features and functions of the product to understand what needs to built and helps estimate its size and what we can deliver.
Privacy impact assessment ("privacy by design" is a core principle). | Engage with Stats NZ privacy officer(s) and Privacy Commission to check for privacy issues, risk areas etc.
JV/partnership(s) | JVs (joint ventures) / partnerships will involve (at minimum) the following elements.
- Identified partner(s) | Identified partner organisations with which to work on building and releasing the product.
- Confirmed at least one partner | At least one confirmed partner organisation.
- Resourcing requirements (roles) | From the Stats NZ, DV and partner(s) sides.
- Early draft commercial documents | Letter of intent / indication of terms/ IP (intellectual property) etc.
Assessment of risks and impacts on Stats NZ /DV / partners | An assessment of any possible risks or impacts for any organisations involved in the venture.
Communications | Any external/internal communications that need to be done to ensure everyone's on side, appropriately informed, etc.
KPIs | KPIs (key performance indicators) are the measurables for the commercial and non-comercial aspects of ventures.
Financial model / forecast | A model / forecast of how the venture's finances will work.
Pitch deck | The output document for all the above criteria.